## Report Results
Full ID | Title | *Number of Devices | *Line of Business | Server Review - Windows: Started | Server Review - Windows: Completed | Power Down - Windows: Started | Power Down - Windows: Completed | Power Down - Windows: Completer
B312-1232678 | Decom_Ashburn_Seom-phase2_02/28/2023 |  | Security | 2023-11-14 17:46:06 | 2023-12-12 13:23:21 | 2024-02-08 16:34:21 | 2024-02-13 09:43:52 | Kathirvel, Madhumitha
B312-1411562 | Decom_DC WestChester_Decom_PACDCMHS01.cable.c_06.12.2023 | 1 | Security | 2023-08-11 15:14:52 | 2023-12-13 13:13:30 | 2023-12-13 20:20:27 | 2024-02-18 09:20:53 | Ahamed, Safeek
B312-1447888 | Decom_WC_SQL03 EOSL Decom_07.17.23 | 2 | BAU | 2023-08-01 01:26:29 | 2024-01-31 07:52:43 | 2024-02-08 15:33:14 | 2024-02-18 15:18:31 | Ahamed, Safeek
B312-1453207 | Decom_WestChester_MSGOMDB_07.21.23 | 2 | GTO | 2024-03-05 16:51:46 | 2024-03-09 08:12:15 | 2024-06-13 16:47:21 | 2024-06-18 14:13:23 | Akkem, Masthan
B312-1456553 | Decom_Chicago_Apex_07.26.23 | 2 | GTO | 2023-11-28 16:21:02 | 2023-12-13 13:17:45 | 2023-12-13 20:23:07 | 2024-01-16 13:25:03 | Ahamed, Safeek
B312-1462380 | Decom_Ashburn_ComcastNow AS_08.01.23 | 1 | GTO | 2023-08-15 16:56:25 | 2023-12-12 13:33:31 | 2023-12-15 14:13:43 | 2024-01-15 14:37:51 | Ahamed, Safeek
B312-1463412 | Decom_CH2_ebzprod_08.01.23 | 7 | GTO | 2023-08-07 18:18:52 | 2024-01-31 08:48:06 | 2024-02-19 17:25:26 | 2024-03-18 09:53:09 | Ahamed, Safeek
B312-1464629 | Decom_Chicago_Decommission-ch2-p1a_ch2-p2a 08.02.23 | 2 | GTO | 2024-04-11 15:29:26 | 2024-04-12 13:37:29 | 2024-06-13 17:29:46 | 2024-06-18 14:15:59 | Akkem, Masthan
B312-1466368 | Decom_Ashburn_Decom MXQ54506QN_08.03.23 | 1 | Enterprise | 2024-02-21 15:54:04 | 2024-03-09 08:16:29 | 2024-06-13 18:12:57 | 2024-06-14 15:26:23 | Ahamed, Safeek
B312-1468726 | Decom_Ashburn_ComcastNow AS_08.07.23 | 2 | GTO | 2023-08-15 17:08:54 | 2023-12-12 13:38:26 | 2024-01-08 14:48:10 | 2024-01-16 09:10:31 | Ahamed, Safeek
B312-1471606 | Decom_potomac_ComcastNow_DB_08.09.2023 | 2 | GTO | 2023-08-29 16:29:23 | 2023-12-12 13:42:46 | 2024-01-26 17:41:31 | 2024-02-05 16:38:30 | Ahamed, Safeek
B312-1493965 | Decom_AS_SQL_INT_8.31.2023 | 3 | GTO | 2024-02-21 15:57:02 | 2024-03-09 08:36:41 | 2024-06-26 23:26:37 | 2024-06-27 07:49:23 | Akkem, Masthan
B312-1493969 | Decom_WC_SQL_INT_08.31.2023 | 3 | GTO | 2023-09-05 16:17:13 | 2023-12-13 13:23:33 | 2024-01-29 18:53:30 | 2024-04-03 09:07:30 | Akkem, Masthan
B312-1493975 | Decom_HO_SQL_INT_08.31.2023 | 1 | GTO | 2023-09-05 16:34:05 | 2023-12-13 13:26:45 | 2024-02-05 21:35:56 | 2024-02-18 11:33:15 | Ahamed, Safeek
B312-1503702 | Decom_WC_SQL_STG_09.13.23 | 6 | GTO | 2023-09-19 13:49:33 | 2024-01-31 08:53:13 | 2024-02-14 20:00:40 | 2024-04-02 10:33:36 | Akkem, Masthan
B312-1506567 | Decom_CH2_SQL_STG_09.15.23 | 7 | GTO | 2023-09-19 14:01:28 | 2024-01-31 09:02:36 | 2024-02-09 16:14:39 | 2024-03-18 10:52:28 | Ahamed, Safeek
B312-1506636 | Decom_PO_SQL_STG_09.15.23 | 4 | GTO | 2023-10-02 18:30:12 | 2024-01-31 09:16:21 | 2024-02-13 14:58:38 | 2024-03-18 11:10:14 | Ahamed, Safeek
B312-1515801 | Decom_EBIZ-WC-Servers_BXT_09262023 | 5 | GTO | 2024-01-02 21:52:12 | 2024-01-11 06:47:46 | 2024-01-29 16:17:07 | 2024-02-18 06:07:11 | Ahamed, Safeek
B312-1515843 | Decom_EBIZ-PO-Servers_BXT_09262023 | 5 | GTO | 2023-11-14 16:11:59 | 2024-01-11 06:52:32 | 2024-01-11 19:06:07 | 2024-02-18 07:19:42 | Ahamed, Safeek
B312-1517022 | Decom_EBIZ_Chicago_6-Servers_BXT_09272023 | 6 | GTO | 2023-10-02 18:14:57 | 2024-01-11 06:56:05 | 2024-01-11 16:34:17 | 2024-02-09 15:28:39 | Jayaraman, Yuvarajan (Contractor)
B312-1520148 | Decom_CAFE_PO-4-DB-Servers_BXT_10022023 | 4 | GTO | 2023-10-02 18:45:56 | 2023-10-11 16:18:00 | 2023-10-11 18:32:02 | 2024-01-11 13:03:33 | Ahamed, Safeek
B312-1520171 | Decom_CAFE_CH2-DB-Servers_BXT_10022023 | 4 | GTO | 2023-10-02 18:23:40 | 2023-10-11 16:29:19 | 2023-10-11 20:23:19 | 2024-01-12 12:22:42 | Ahamed, Safeek
B312-1532976 | Decom_NDC Chicago_gisfil-ch2-a1p.cable.com_10.16.23 | 1 | GTO | 2023-10-30 15:54:33 | 2023-12-12 13:48:05 | 2024-01-02 17:03:06 | 2024-02-13 12:47:58 | Ahamed, Safeek
B312-1544103 | Decom_EBIZ-WC-Servers_BXT_10262023 | 3 | GTO | 2023-10-30 16:13:12 | 2024-01-11 07:00:34 | 2024-01-29 19:21:11 | 2024-01-31 09:29:29 | Kathirvel, Madhumitha
B312-1552705 | Decom_Chicago_AMAG_11.07.23 | 2 | Security | 2024-04-22 14:58:53 | 2024-04-23 07:32:06 | 2024-05-23 13:57:23 | 2024-05-23 15:02:51 | Akkem, Masthan
B312-1552706 | Decom_Ashburn_AMAG_11.07.23 | 3 | Security | 2024-08-08 13:51:54 | 2024-08-08 13:51:58 | 2024-08-08 13:52:08 | 2024-08-08 13:52:13 | Young, Michael
B312-1552942 | Decom_CH2_Records Management_11.07.23 | 4 | BAU | 2023-11-28 16:53:55 | 2023-12-13 13:47:42 | 2023-12-14 17:04:40 | 2024-03-18 11:44:43 | Ahamed, Safeek
B312-1556432 | Decom_WC_sql03decom_11.10.23 | 1 | Xfinity | 2023-11-14 16:38:02 | 2023-11-30 15:47:48 | 2024-01-02 15:00:05 | 2024-01-16 11:17:02 | Ahamed, Safeek
B312-1557354 | Decom_West Chester_Decom_VMS_Servers_2_11/13/2023 | 2 | Security | 2024-01-25 14:09:14 | 2024-01-31 10:07:59 | 2024-01-31 18:38:40 | 2024-04-03 12:27:02 | Akkem, Masthan
B312-1557357 | Decom_Chicago_Decom_VMS_Servers_2_11/13/2023 | 2 | Security | 2024-01-25 14:09:06 | 2024-02-05 16:05:01 | 2024-02-05 16:31:01 | 2024-03-09 11:40:11 | Ahamed, Safeek
B312-1564896 | Decom_Ashburn_Decom_epsprd-as-1p_11.21.23 | 1 | Advertising | 2023-11-28 17:22:22 | 2024-02-06 11:08:57 | 2024-02-07 18:29:36 | 2024-02-22 15:35:30 | Herrick, Deborah
B312-1565041 | Decom_Hillsboro_Decom_CSMWEB-HO-3P_11.21.23 | 1 | Advertising | 2023-11-27 19:22:39 | 2023-12-13 13:54:10 | 2023-12-15 22:35:18 | 2024-01-12 18:39:26 | Herrick, Deborah
B312-1580849 | Decom_Chicago_Old_G7_Hosts_12.12.23 | 2 | GTO | 2024-01-08 19:03:42 | 2024-02-05 11:54:06 | 2024-02-14 10:14:03 | 2024-02-14 10:14:44 | Kathirvel, Madhumitha
B312-1585211 | Decom_Westchester_WC Decom and ship to HO_12.15.23 | 4 | GTO | 2023-12-19 17:41:48 | 2023-12-19 17:41:52 | 2024-01-03 19:45:52 | 2024-01-03 19:45:56 | Mathew, Bijo (Contractor)
B312-1588904 | Decom_AS_CN_DB_12.21.23 | 3 | GTO | 2024-02-27 17:08:18 | 2024-03-09 06:50:31 | 2024-03-21 16:13:06 | 2024-03-29 10:32:29 | Akkem, Masthan
B312-1588905 | Decom_PO_CN_DB_12.21.23 | 2 | GTO | 2024-01-08 19:14:30 | 2024-01-15 14:01:12 | 2024-02-08 17:07:43 | 2024-02-13 08:39:00 | Kathirvel, Madhumitha
B312-1588906 | Decom_HO_CN_DB_12.21.23 | 2 | GTO | 2024-01-08 19:26:56 | 2024-01-15 14:07:37 | 2024-02-19 14:06:12 | 2024-03-09 10:21:01 | Ahamed, Safeek
B312-1588907 | Decom_Potomac_Decom_old_G7_hosts_12.21.23 | 1 | GTO | 2024-01-08 19:16:42 | 2024-02-05 12:10:46 | 2024-02-05 16:07:26 | 2024-02-14 09:49:03 | Kathirvel, Madhumitha
B312-1588910 | Decom_Hillsboro_ADFS_Decommission_12.21.23 | 6 | GTO | 2024-01-05 20:42:14 | 2024-01-05 20:42:17 | 2024-01-05 20:42:19 | 2024-01-29 19:56:03 | Young, Michael
B312-1589907 | Decom_Westchester_Old_G7_WC_Hosts_12.22.23 | 1 | GTO | 2024-01-08 19:31:50 | 2024-02-05 12:19:27 | 2024-02-05 16:18:29 | 2024-02-22 12:50:02 | mote, shravan (Contractor)
B312-1592964 | Decom_BXT_CBH_Chicago server_cbhdb2-ch2-1p_01022024 | 1 | GTO | 2024-01-24 13:49:16 | 2024-02-06 11:24:17 | 2024-02-07 19:06:12 | 2024-04-03 12:36:21 | Akkem, Masthan
B312-1596457 | Decom_PTB_ccsmgr-ptb-p49_01.05.24 | 1 | Security | 2024-02-06 16:25:49 | 2024-02-13 07:25:50 | 2024-02-13 19:55:42 | 2024-02-17 12:16:26 | Ahamed, Safeek
B312-1597197 | Decom_NDC - Chicago_Decom_CH2_CI_CMDB_RTDB_1/5/2024 | 10 | GTO | 2024-01-25 19:18:31 | 2024-02-06 11:32:58 | 2024-02-28 22:58:49 | 2024-04-03 13:31:16 | Akkem, Masthan
B312-1597221 | Decom_NDC - West_Chester_WC_DECOM_CMS_TFS_1/5/2024 | 11 | GTO | 2024-01-30 16:02:31 | 2024-02-06 11:39:34 | 2024-02-13 18:53:41 | 2024-04-02 13:17:32 | Akkem, Masthan
B312-1597227 | Decom_NDC - Potomac_Decom_Potomac_CMS_1/5/2024 | 2 | GTO | 2024-01-25 20:23:00 | 2024-01-31 07:27:56 | 2024-02-13 19:40:48 | 2024-03-26 08:56:08 | Ahamed, Safeek
B312-1597246 | Decom_NDC - Ashburn_Ashburn_Decom_RTDB_CMCDB_1/5/2024 | 7 | GTO | 2024-01-30 17:00:37 | 2024-01-31 07:17:35 | 2024-02-26 15:34:40 | 2024-04-01 11:16:36 | Akkem, Masthan
B312-1597252 | Decom_NDC - Hillsboro_Hillsboro_Decom_CMDB_CMS_1/5/2024 | 11 | GTO | 2024-02-20 16:57:42 | 2024-03-09 08:40:32 | 2024-06-23 23:29:50 | 2024-06-27 07:31:11 | Akkem, Masthan
B312-1600403 | Decom_Potomac_WCDecom_01.09.24 | 1 | BAU | 2024-01-11 18:09:53 | 2024-01-15 14:09:23 | 2024-01-16 15:32:21 | 2024-01-25 06:29:49 | Kathirvel, Madhumitha
B312-1601259 | Decom_Ashburn_SEPM as-a04p_01/10/2024 | 1 | Security | 2024-02-21 15:51:28 | 2024-03-01 07:28:34 | 2024-03-01 07:28:34 | 2024-03-01 07:41:00 | Ahamed, Safeek
B312-1602024 | Decom_Potomac_GisMapping_01.11.24 | 7 | BAU | 2024-04-09 17:18:54 | 2024-04-09 17:22:05 | 2024-05-17 08:11:24 | 2024-05-17 08:12:22 | Duraimanickam, Rengaraja
B312-1603747 | Decom_WesterChester_Decom Request_01.21.24 | 2 | GTO | 2024-02-07 17:26:43 | 2024-02-17 10:57:18 | 2024-06-14 14:37:18 | 2024-06-18 13:12:07 | Ahamed, Safeek
B312-1604029 | Decom_Chicago_Decom Request_01.12.24 | 2 | GTO | 2024-01-31 17:01:41 | 2024-02-06 12:32:48 | 2024-02-14 16:09:29 | 2024-03-26 09:55:06 | Ahamed, Safeek
B312-1606783 | Decom_BXT_BDI_Potomac_Q01_01172024 | 1 | GTO | 2024-01-24 13:42:35 | 2024-01-29 04:18:12 | 2024-01-29 15:29:38 | 2024-01-31 07:17:37 | Kathirvel, Madhumitha
B312-1617030 | Decom_Hillsboro_Gis Mapping_01.29.24 | 1 | BAU | 2024-04-09 11:03:01 | 2024-04-10 06:58:05 | 2024-05-17 08:11:52 | 2024-05-17 08:12:01 | Duraimanickam, Rengaraja
B312-1617390 | Decom_ASH_ADCON_DL360_Gen_9_01.29.24 | 1 | GTO | 2024-01-31 16:55:47 | 2024-02-06 12:37:49 | 2024-02-07 19:14:53 | 2024-03-09 12:05:00 | Ahamed, Safeek
B312-1620661 | Decom_WC_Eracent DB Servers_02.01.2024 | 2 | GTO | 2024-02-05 15:37:02 | 2024-02-05 16:00:15 | 2024-02-09 15:19:22 | 2024-02-17 12:56:23 | Ahamed, Safeek
B312-1621734 | Decom_NDC - West_Chester_Decom WC LGDB and RTDB_1/22024 | 4 | GTO | 2024-02-05 15:41:40 | 2024-02-17 10:52:20 | 2024-07-15 21:20:57 | 2024-07-17 12:49:38 | Akkem, Masthan
B312-1621942 | Decom_NDC - Chicago_Decom CH LGDB and RTDB_1/2/2024 | 4 | GTO | 2024-02-05 17:56:20 | 2024-03-13 07:52:52 | 2024-07-15 21:21:00 | 2024-07-17 12:51:10 | Akkem, Masthan
B312-1621960 | Decom_NDC - Potomac_Decom PO LGDB and RTDB_1/2/2024 | 4 | GTO | 2024-02-26 16:53:50 | 2024-03-09 09:01:59 | 2024-04-08 14:12:55 | 2024-04-09 09:49:08 | Ahamed, Safeek
B312-1625019 | Decom_Potomac_srcjump_po-01p_02.06.2024 | 1 | Security | 2024-02-07 17:24:33 | 2024-02-13 10:05:12 | 2024-02-13 14:21:10 | 2024-03-12 05:54:52 | Kathirvel, Madhumitha
B312-1625214 | Decom_AS_CN_APP_07.02.2024 | 2 | GTO | 2024-02-20 16:32:27 | 2024-03-09 07:18:36 | 2024-03-21 16:29:27 | 2024-04-01 12:03:41 | Akkem, Masthan
B312-1628796 | Decom_West Chester_nco01db-wc-01p Decom_02/10/24 | 1 | BAU | 2024-02-27 17:22:58 | 2024-03-09 09:05:30 | 2024-05-24 16:57:18 | 2024-05-27 07:37:58 | Akkem, Masthan
B312-1641044 | Decom_AS_FraudView_02-23-2024 | 2 | Xfinity | 2024-04-23 05:39:23 | 2024-04-23 07:41:20 | 2024-06-18 06:47:19 | 2024-06-18 09:36:53 | Akkem, Masthan
B312-1645762 | Decom_West Chester_srcjump_wc_01p_02.28.2024 | 1 | Security | 2024-03-05 16:55:08 | 2024-03-09 07:56:12 | 2024-04-17 14:07:05 | 2024-04-17 17:03:17 | Negron, Pedro
B312-1648488 | Decom_Decom_West Chester DC_Proliant DL360p Gen8_03.01.24 | 2 | GTO | 2024-03-05 17:01:44 | 2024-03-13 08:08:21 | 2024-07-15 21:22:26 | 2024-07-17 12:53:16 | Akkem, Masthan
B312-1649328 | Decom_NDC - Potomac_Decom PO RT and CM_3/4/2024 | 4 | Xfinity | 2024-03-05 19:39:46 | 2024-03-18 08:50:41 | 2024-06-11 15:48:38 | 2024-06-18 13:50:26 | Akkem, Masthan
B312-1658440 | Decom_WC_NDC_03.13.24 | 2 | Security | 2024-03-14 02:22:01 | 2024-03-16 10:33:40 | 2024-04-19 14:34:45 | 2024-04-22 08:20:29 | Akkem, Masthan
B312-1661866 | Decom_NDC - Chicago_Decom-CH2-March-2024_3/15/2024 | 4 | Xfinity | 2024-03-18 16:23:16 | 2024-03-22 07:58:42 | 2024-06-12 15:49:45 | 2024-06-13 10:47:46 | B, Mukesh
B312-1661876 | Decom_NDC - West_Chester_Decom-WC-March-2024_3/15/2024 | 4 | Xfinity | 2024-03-18 16:31:49 | 2024-03-26 08:17:31 | 2024-06-11 15:00:45 | 2024-06-13 14:21:19 | B, Mukesh
B312-1661881 | Decom_NDC - Potomac_Decom-PO-March-2024_3/15/2024 | 4 | Xfinity | 2024-03-17 18:03:47 | 2024-04-01 11:33:13 | 2024-07-15 21:26:34 | 2024-07-17 12:56:14 | Akkem, Masthan
B312-1661888 | Decom_NDC - Hillsboro_Decom-HO-March-2024_3/15/2024 | 1 | Xfinity | 2024-03-18 16:34:21 | 2024-04-01 11:37:49 | 2024-07-15 21:26:37 | 2024-07-17 12:57:44 | Akkem, Masthan
B312-1664578 | Decom_Testing_Please_Ignoredd | 23 | Division (Central) | 2024-03-19 20:10:13 | 2024-03-19 20:10:15 | 2024-03-19 20:10:25 | 2024-03-19 20:10:28 | Heaton, Chris
B312-1669354 | Decom_NDC - West_Chester_Decom WC cmdb_3/25/2024 | 2 | Xfinity | 2024-03-26 19:02:14 | 2024-04-02 08:40:09 | 2024-06-06 16:19:32 | 2024-06-11 09:31:52 | B, Mukesh
B312-1669364 | Decom_NDC - Potomac_Decom PO cmdb_3/25/2024 | 2 | Xfinity | 2024-03-26 15:13:32 | 2024-04-01 11:49:53 | 2024-06-06 16:35:25 | 2024-06-11 10:02:25 | B, Mukesh
B312-1670284 | Decom_DC Westchester_NCOE Server Decommission_26/3/2024 | 3 | Other | 2024-05-22 14:21:03 | 2024-05-22 14:40:29 | 2024-07-15 21:26:48 | 2024-07-17 12:46:17 | Akkem, Masthan
B312-1671180 | Decom_Ashburn_Decom_SCTASK0908523_ADM_03.26.24 | 2 | Advertising | 2024-03-28 15:00:23 | 2024-04-02 09:27:39 | 2024-07-15 21:26:51 | 2024-07-17 13:01:36 | Akkem, Masthan
B312-1672077 | Oprepdb-as-6p_Decom_SCTASK0890276 | 1 | Advertising | 2024-03-28 15:02:48 | 2024-04-02 09:40:17 | 2024-07-15 21:26:56 | 2024-07-17 13:06:06 | Akkem, Masthan
B312-1673020 | Decom_WC_NDC_MDEVDB_03.28.2024 | 1 | Security | 2024-04-02 16:06:55 | 2024-04-03 08:00:27 | 2024-04-29 20:57:04 | 2024-04-30 10:12:39 | Akkem, Masthan
B312-1674075 | Decom_Hillsboro_MPVNTG-HO-01S_Decom_03.28.24 | 1 | Advertising | 2024-04-02 15:26:11 | 2024-04-03 08:06:08 | 2024-07-15 21:26:59 | 2024-07-17 13:11:55 | Akkem, Masthan
B312-1675906 | Decom_Chicago NDC_PAM vlts decom_04.01.24 | 4 | Security | 2024-04-09 17:36:54 | 2024-04-10 07:06:13 | 2024-07-05 16:32:13 | 2024-07-09 09:33:35 | B, Mukesh
B312-1677055 | Decom_Ashburn_E360_4/2/2024 | 4 | Comcast Business Services | 2024-04-18 13:37:37 | 2024-04-22 12:14:06 | 2024-04-29 05:54:15 | 2024-04-29 05:54:21 | Balaguru, Krithick (Contractor)
B312-1677799 | Decom_Ashburn NDC_PAM vlts decom_04.02.24 | 4 | Security | 2024-04-09 17:31:49 | 2024-04-10 07:11:34 | 2024-07-15 21:29:40 | 2024-07-17 13:08:19 | Akkem, Masthan
B312-1677838 | Decom_Hillsboro_NDC_PAM vlts decom_04.02.24 | 2 | Security | 2024-04-09 14:49:06 | 2024-04-10 08:36:57 | 2024-07-05 16:40:50 | 2024-07-09 09:35:50 | B, Mukesh
B312-1679493 | Decom_WC_Dlpmdb_04.04.2024 | 1 | Security | 2024-04-04 15:51:50 | 2024-04-05 06:46:43 | 2024-04-29 21:05:04 | 2024-04-30 09:52:28 | Akkem, Masthan
B312-1692583 | Decom_Beaverton_decom_ccsmgr-bv-p46-con_04.18.24 | 1 | Security | 2024-04-20 19:22:12 | 2024-04-22 07:57:43 | 2024-04-30 14:12:12 | 2024-05-06 11:57:01 | Akkem, Masthan
B312-1692586 | Decom_Beaverton_decom_ccsmgr-bv-p47-con_04.18.24 | 1 | Security | 2024-04-20 19:16:28 | 2024-04-22 08:01:31 | 2024-04-30 14:35:52 | 2024-05-06 12:03:54 | Akkem, Masthan
B312-1680617 | Decom_Chicago_suptr_04.05.24 | 1 | Other | 2024-04-09 17:39:16 | 2024-04-10 08:48:03 | 2024-07-15 21:27:04 | 2024-07-17 13:39:10 | Akkem, Masthan
B312-1681477 | Decom_HO_STARDB Decommission_04.05.24 | 1 | Voice | 2024-04-11 15:36:28 | 2024-04-16 07:36:13 | 2024-07-15 21:27:07 | 2024-07-17 13:40:16 | Akkem, Masthan
B312-1681495 | Decom_AS_STARDB Decom_04.05.24 | 1 | Voice | 2024-04-11 15:38:43 | 2024-04-16 07:39:02 | 2024-07-15 21:27:09 | 2024-07-17 13:41:38 | Akkem, Masthan
B312-1682929 | Decom_Potomac_E360_4/8/2024 | 3 | Comcast Business Services | 2024-05-16 05:57:06 | 2024-05-16 05:57:12 | 2024-05-16 05:58:38 | 2024-05-16 05:58:59 | Balaguru, Krithick (Contractor)
B312-1682956 | Decom_West_Chester_E360_4/8/2024 | 3 | Comcast Business Services | 2024-04-18 13:38:55 | 2024-04-22 12:21:11 | 2024-04-29 06:01:28 | 2024-04-29 06:01:41 | Balaguru, Krithick (Contractor)
B312-1684137 | Decom_Chicago_Commtax UI 7322_040924 | 2 | Comcast Business Services | 2024-06-05 18:24:42 | 2024-06-06 07:51:14 | 2024-06-06 20:18:45 | 2024-06-10 10:29:00 | Ahamed, Safeek
B312-1696850 | Decom_Westchester_ADFS server DECOMM_04.23.24 | 2 | GTO | 2024-04-30 17:06:53 | 2024-05-06 11:46:03 | 2024-07-15 21:28:17 | 2024-07-17 13:54:51 | Akkem, Masthan
B312-1697381 | Decom_Ashburne_Briefcamm_4.23.24 | 4 | Security | 2024-04-24 13:11:08 | 2024-05-07 13:21:01 | 2024-05-07 13:21:02 | 2024-05-07 14:34:13 | Akkem, Masthan
B312-1698644 | Decom_PO_DLPDAR_4.25.24 | 12 | Security | 2024-04-25 19:51:41 | 2024-04-26 14:56:26 | 2024-04-30 15:52:51 | 2024-05-07 14:09:39 | Akkem, Masthan
B312-1698645 | Decom_WC_DLPDAR_04.25.2024 | 30 | Security | 2024-04-25 12:26:31 | 2024-04-25 14:26:17 | 2024-05-03 20:28:30 | 2024-05-08 08:22:47 | Akkem, Masthan
B312-1698649 | Decom_AS_DLP DAR_4.25.24 | 10 | Security | 2024-04-25 13:05:08 | 2024-04-25 14:34:45 | 2024-04-30 17:15:13 | 2024-05-07 15:41:58 | Ahamed, Safeek
B312-1698651 | Decom_CH_DLP DAR_4.25.24 | 10 | Security | 2024-04-25 19:37:01 | 2024-04-26 14:59:52 | 2024-04-29 18:42:57 | 2024-05-08 12:06:41 | Ahamed, Safeek
B312-1700612 | Decom_AS_DLP DAR_4.29.24 | 6 | Security | 2024-04-29 12:53:48 | 2024-04-30 08:02:16 | 2024-04-30 20:02:18 | 2024-05-07 14:04:43 | Ahamed, Safeek
B312-1700621 | Decom_WC_NDC_04.29.2024 | 3 | Security | 2024-04-29 15:12:30 | 2024-04-30 08:06:14 | 2024-04-30 19:42:52 | 2024-05-06 12:11:09 | Ahamed, Safeek
B312-1700627 | Decom_CH_NDC_04.29.2024 | 2 | Security | 2024-04-29 15:00:05 | 2024-04-30 08:13:19 | 2024-04-30 19:07:44 | 2024-05-07 13:41:01 | Ahamed, Safeek
B312-1700851 | Decom_NDC - Chicago_Decom_CH2_cddb_4/29/2024 | 2 | Xfinity | 2024-04-29 15:02:20 | 2024-04-30 09:10:07 | 2024-07-08 19:13:19 | 2024-07-09 10:40:23 | B, Mukesh
B312-1700883 | Decom_NDC - West_Chester_Decom-cddb-wc_4/29/2024 | 2 | Xfinity | 2024-04-29 15:15:15 | 2024-04-30 09:13:59 | 2024-07-08 19:38:28 | 2024-07-09 12:35:44 | B, Mukesh
B312-1700912 | Decom_NDC - Potomac_Decom_cddb-po_4/29/2024 | 2 | Xfinity | 2024-04-29 15:09:13 | 2024-04-30 09:21:52 | 2024-07-08 19:50:59 | 2024-07-09 12:56:16 | B, Mukesh
B312-1703371 | Decom_PO_STARDB Decommission_05.01.2024 | 1 | Voice | 2024-05-01 17:57:39 | 2024-05-06 11:43:04 | 2024-07-15 21:28:32 | 2024-07-17 13:44:11 | Akkem, Masthan
B312-1705798 | Decom_CMC_DLP_DAR_3.5.24 | 5 | Security | 2024-05-07 15:42:42 | 2024-05-07 15:47:17 | 2024-05-08 14:04:28 | 2024-05-09 15:43:53 | Ahamed, Safeek
B312-1714718 | Decom_PO_PEVSTR DECOM_05.14.24 | 1 | Voice | 2024-05-16 17:15:53 | 2024-05-20 11:10:22 | 2024-07-15 21:30:08 | 2024-07-17 13:45:20 | Akkem, Masthan
B312-1714735 | Decom_AS_PEVSTR2 DECOM_05.14.24 | 1 | Voice | 2024-05-16 15:42:07 | 2024-05-17 10:26:37 | 2024-07-15 21:30:10 | 2024-07-17 13:45:53 | Akkem, Masthan
B312-1721297 | Decom_CH2/Northlake_Relocate Blades/Servers_5.22.24 | 6 | GTO | 2024-10-30 15:38:48 | 2024-11-01 04:55:50 | 2024-11-01 13:47:37 | 2024-11-04 06:24:09 | Akkem, Masthan
B312-1722526 | Decom_POTOMAC_Stage EPM_5/23/24 | 8 | GTO | 2024-06-05 16:09:38 | 2024-06-06 09:12:00 | 2024-07-01 19:49:55 | 2024-07-10 12:47:51 | Akkem, Masthan
B312-1723801 | Decom_NDC - Potomac_decom_PO_codb_5/24/2024 | 2 | Xfinity | 2024-05-29 16:54:50 | 2024-05-30 07:36:23 | 2024-07-15 21:30:26 | 2024-07-17 13:53:35 | Akkem, Masthan
B312-1723807 | Decom_NDC - West_Chester_decom_WC_codb_5/24/2024 | 2 | Xfinity | 2024-05-29 17:03:06 | 2024-05-30 07:41:45 | 2024-07-15 21:30:28 | 2024-07-17 13:47:56 | Akkem, Masthan
B312-1723816 | Decom_NDC - Chicago_decom_CH2_codb_5/24/2024cccccbkbtvrctfd | 2 | Xfinity | 2024-05-28 15:28:56 | 2024-05-29 11:58:48 | 2024-07-15 21:30:30 | 2024-07-17 13:48:47 | Akkem, Masthan
B312-1724583 | Decom_Ashburn_Decom_CSM_SCTASK1086385_05.28.24 | 2 | Advertising | 2024-06-03 16:27:40 | 2024-06-03 16:37:28 | 2024-07-15 21:30:33 | 2024-07-17 13:55:00 | Akkem, Masthan
B312-1724673 | Decom_Hillsboro_Decom_CSMAPP-HO-7P_05.28.24 | 1 | Advertising | 2024-06-04 15:10:50 | 2024-06-06 07:46:17 | 2024-07-15 21:30:36 | 2024-07-17 13:50:50 | Akkem, Masthan
B312-1725082 | Decom_Ashburn_Decom_legacy_Verint_App_05.28.24 | 4 | Other | 2024-06-03 16:30:23 | 2024-06-03 16:43:35 | 2024-06-06 20:33:09 | 2024-06-10 09:50:55 | Ahamed, Safeek
B312-1729044 | Decom_AS_DLP LAB_6.3.24 | 5 | Security | 2024-06-03 16:59:39 | 2024-06-04 11:27:13 | 2024-06-10 14:01:08 | 2024-06-11 07:49:43 | Akkem, Masthan
B312-1730346 | Decom_Ashburn_Prod_EPM_6/3/24 | 8 | GTO | 2024-06-05 16:12:49 | 2024-06-06 13:53:30 | 2024-07-01 20:26:10 | 2024-07-10 12:32:09 | Akkem, Masthan
B312-1735245 | Decom_WC_DLP NM_6.10.24 | 6 | Security | 2024-06-10 17:08:45 | 2024-06-11 07:28:30 | 2024-06-12 16:39:17 | 2024-06-18 12:39:15 | B, Mukesh
B312-1735246 | Decom_PO_DLP NM_6.10.24 | 4 | Security | 2024-06-10 17:16:04 | 2024-06-11 07:54:22 | 2024-06-12 16:18:31 | 2024-06-13 16:38:45 | B, Mukesh
B312-1735248 | Decom_AS_DLP NM_6.10.24 | 1 | Security | 2024-06-10 17:19:06 | 2024-06-11 08:37:41 | 2024-06-12 15:59:08 | 2024-06-12 16:27:04 | B, Mukesh
B312-1735249 | Decom_HO_DLP NM_6.10.24 | 1 | Security | 2024-06-10 17:22:02 | 2024-06-11 07:16:18 | 2024-06-11 16:04:50 | 2024-06-14 14:57:03 | Ahamed, Safeek
B312-1735250 | Decom_CH_DLP NM_6.10.24 | 1 | Security | 2024-06-12 16:33:11 | 2024-06-13 10:27:30 | 2024-06-13 14:25:36 | 2024-06-17 11:26:54 | B, Mukesh
B312-1743744 | Decom_AS_DAR-Enf_6.19.24 | 1 | Security | 2024-06-24 19:13:38 | 2024-06-25 13:27:50 | 2024-06-27 13:33:18 | 2024-06-28 11:50:14 | Akkem, Masthan
B312-1745774 | Decom_AS_PEVSTR3 DECOM_06.21.24 | 1 | Voice | 2024-06-24 19:15:53 | 2024-06-25 13:28:17 | 2024-07-15 21:30:58 | 2024-07-17 13:51:32 | Akkem, Masthan
B312-1750589 | Decom_Ashburn_Decom_legacy_Verint_06.26.24 | 3 | Other | 2024-07-02 16:11:21 | 2024-07-04 09:26:02 | 2024-07-09 16:37:45 | 2024-07-10 13:03:26 | Akkem, Masthan
B312-1752795 | Decom_NDC - Chicago_Decom EBZCMS-CH2-2I_6/28/2024 | 1 | Xfinity | 2024-07-02 15:18:31 | 2024-07-04 09:29:16 | 2024-07-17 13:53:58 | 2024-07-17 13:54:20 | Akkem, Masthan
B312-1753616 | Decom_CH_WPIB_7.1.24 | 10 | Security | 2024-07-02 15:21:21 | 2024-07-04 09:23:22 | 2024-07-09 18:48:01 | 2024-07-10 13:15:09 | Akkem, Masthan
B312-1753629 | Decom_HO_WP-IB_7.1.24 | 10 | Security | 2024-07-02 15:58:48 | 2024-07-04 09:41:12 | 2024-07-09 17:16:46 | 2024-07-11 08:28:05 | Akkem, Masthan
B312-1753657 | Decom_AS_DLP _7.1.24 | 12 | Security | 2024-07-02 15:03:15 | 2024-07-04 09:37:20 | 2024-07-08 17:38:28 | 2024-07-09 13:56:29 | B, Mukesh
B312-1753669 | Decom_PO_DLP_7.1.24 | 6 | Security | 2024-07-02 04:52:51 | 2024-07-04 09:31:22 | 2024-07-10 06:43:21 | 2024-07-11 08:25:39 | Akkem, Masthan
B312-1753713 | Decom_WC_DLP_7.1.24 | 13 | Security | 2024-07-10 07:36:57 | 2024-07-11 08:39:04 | 2024-07-16 04:37:23 | 2024-07-17 12:43:33 | Akkem, Masthan
B312-1761512 | Decom_wc_decom_digitalServers_10072024 | 2 | GTO | 2025-01-16 19:00:53 | 2025-01-16 19:01:01 | 2025-01-16 19:01:11 | 2025-01-16 19:01:19 | Manikanta, Karanam (Contractor)
B312-1764199 | Decom_Westchester_NPS_Proliant_DL360_G8-9_07.12.24 | 3 | GTO | 2024-07-22 17:16:46 | 2024-07-31 13:25:48 | 2024-08-02 13:55:39 | 2024-08-27 06:55:44 | Akkem, Masthan
B312-1764244 | Decom_Potomac_NPS_Proliant_DL360_G8_07.12.24 | 1 | GTO | 2024-07-22 17:00:33 | 2024-07-31 13:29:09 | 2024-08-02 13:55:30 | 2024-08-27 06:55:03 | Akkem, Masthan
B312-1783419 | Decom_Hillsboro_Verint EXM Decomm_08/02/24 | 1 | Other | 2025-04-17 17:16:49 | 2025-04-18 09:32:38 | 2025-06-16 17:45:31 | 2025-06-17 07:41:26 | Akkem, Masthan
B312-1789086 | Decom_AS_DLP DAR_8.9.24 | 1 | Security | 2024-08-13 20:22:39 | 2024-08-23 06:59:17 | 2024-08-23 06:59:18 | 2024-08-23 07:02:55 | Akkem, Masthan
B312-1789434 | Decom_AS_repurpose_servers_08.09.24 | 3 | Other | 2024-08-12 16:13:39 | 2024-08-27 06:45:47 | 2024-09-06 08:10:24 | 2024-09-12 06:48:55 | Akkem, Masthan
B312-1790329 | Decom_AS_NSO LAB_08.12.24 | 1 | Security | 2024-11-06 04:59:17 | 2024-11-06 10:24:04 | 2024-11-07 06:35:07 | 2024-11-07 07:44:42 | Kathirvel, Madhumitha
B312-1797233 | Decom_West Chester_PA EdgeRelay decom_08.13.24 | 2 | GTO | 2024-12-09 15:42:02 | 2024-12-10 08:35:11 | 2024-12-10 08:35:12 | 2024-12-10 08:41:54 | Akkem, Masthan
B312-1892101 | Decom_HO_Decom_ncodb4-ho-01a_08.21.24 | 2 | Other | 2024-09-23 14:46:08 | 2024-09-30 08:30:22 | 2024-10-03 15:12:57 | 2024-10-08 07:03:43 | Akkem, Masthan
B312-2420061 | Decom_ch_dlpdar_9.5.24 | 1 | Security | 2024-09-12 18:26:24 | 2024-09-16 12:42:32 | 2024-09-16 12:42:33 | 2024-09-16 12:45:46 | Akkem, Masthan
B312-2420173 | Decom_HO_dlpwp_9.5.24 | 5 | Security | 2024-09-11 19:19:36 | 2024-09-12 06:56:02 | 2024-09-12 06:56:03 | 2024-09-12 06:58:30 | Akkem, Masthan
B312-2421024 | Decom_AS_dlpwp_9.5.24 | 6 | Security | 2024-09-10 13:54:47 | 2024-09-12 06:56:15 | 2024-09-12 06:56:15 | 2024-09-12 06:58:56 | Akkem, Masthan
B312-2423005 | Decom_Hillsboro_GIS Mapping_09.10.24 | 9 | PLEX | 2024-09-23 14:51:33 | 2024-09-30 08:38:11 | 2024-09-30 09:53:46 | 2024-10-03 09:21:27 | Akkem, Masthan
B312-2425330 | Decom_CH2_CADA_0911 | 1 | Security | 2024-09-23 14:33:07 | 2024-09-30 08:26:56 | 2024-09-30 08:26:57 | 2024-09-30 08:50:51 | Akkem, Masthan
B312-2454990 | Decom_spotqa-as-1p-con.cable.c_TSGQA_09.24.24 | 1 | Other | 2024-10-21 18:00:32 | 2024-10-22 07:24:56 | 2024-10-22 07:24:56 | 2024-10-22 07:54:33 | Kathirvel, Madhumitha
B312-2455013 | Decom_spotperf-as-4p-con.cable_TSGQA_09.24.24 | 1 | Other | 2024-10-21 18:04:20 | 2024-10-22 07:27:55 | 2024-10-22 07:27:55 | 2024-10-22 07:56:33 | Kathirvel, Madhumitha
B312-2459111 | Decom_CH2_NSO LAB_30.09.2024 | 1 | Security | 2024-11-07 06:26:24 | 2024-11-07 07:36:04 | 2024-11-07 09:34:33 | 2024-11-07 13:17:10 | Kathirvel, Madhumitha
B312-2467186 | Decom_AS_Servers_decom_2024.10.09 | 4 | GTO | 2024-12-03 04:15:06 | 2024-12-04 12:17:20 | 2024-12-05 09:21:16 | 2024-12-05 09:30:38 | Akkem, Masthan
B312-2467656 | Decom_CH_server_decom_2024.10.09 | 19 | GTO | 2025-01-24 03:22:51 | 2025-01-28 12:27:45 | 2025-01-29 06:22:46 | 2025-01-29 09:49:11 | Akkem, Masthan
B312-2467710 | Decom_PO_Servers_decom_2024.10.09 | 6 | GTO | 2025-01-23 18:31:59 | 2025-01-28 12:40:37 | 2025-01-28 12:40:37 | 2025-01-28 12:43:37 | Akkem, Masthan
B312-2472162 | Decom_Potomac_Decom Ilex 2 PO Servers_10/16/2024 | 2 | GTO | 2025-01-19 16:56:50 | 2025-01-27 10:41:40 | 2025-01-27 10:41:41 | 2025-01-27 10:41:55 | Chakraborty, Siddhartha (Contractor)
B312-2474561 | Decom_Ashburn_tabapp-as-a6p_10.17.24 | 1 | GTO | 2025-01-21 16:24:30 | 2025-01-22 10:00:10 | 2025-01-22 10:00:11 | 2025-01-22 10:01:04 | Akkem, Masthan
B312-2475391 | Decom_Hillsboro_cbpcdb-ho-p01c Server_10/18/2024 | 1 | GTO | 2024-10-25 18:04:44 | 2024-11-01 08:00:32 | 2024-11-01 08:00:32 | 2024-11-01 08:07:26 | Akkem, Masthan
B312-2477417 | Decom_DCF_Vimbiz-CTSBE_10/22/2024 | 2 | CTS | 2024-10-26 22:39:13 | 2024-11-01 07:56:23 | 2024-11-06 06:08:49 | 2024-11-14 07:40:29 | Akkem, Masthan
B312-2467155 | Decom_WEST CHESTER_Multiple_server_decom_2024.10.09 | 11 | GTO | 2024-11-25 10:36:40 | 2024-11-25 11:47:22 | 2024-11-27 08:15:51 | 2024-11-27 09:16:01 | Akkem, Masthan
B312-2471730 | Decom_westchester_Ontrac_P07A_Decommission_10/15/2024 | 1 | Other | 2025-03-11 13:21:54 | 2025-03-14 05:56:41 | 2025-03-25 08:11:46 | 2025-03-26 11:08:51 | Akkem, Masthan
B312-2489837 | Decom_AS_Repurpose_servers_11.06.24 | 2 | Other | 2024-12-03 18:00:08 | 2024-12-04 12:21:07 | 2024-12-04 12:21:07 | 2024-12-04 12:24:19 | Akkem, Masthan
B312-2520161 | Decom_Ashburn_Decom FORELABS Primary_16-Dec-2024 | 1 | Other | 2025-06-09 16:44:11 | 2025-06-10 08:39:16 | 2025-06-10 08:39:16 | 2025-06-10 08:40:45 | Akkem, Masthan
B312-2508228 | Decom_Ashburn_Legacy_NCO_Verint_12.03.24 | 6 | Other | 2025-01-21 16:46:38 | 2025-01-28 12:49:23 | 2025-02-07 16:33:35 | 2025-02-11 10:18:17 | Akkem, Masthan
B312-2508323 | Decom_Hillsboro_Legacy_NCO_Verint_12.03.24 | 5 | Other | 2024-12-11 22:44:20 | 2025-01-06 07:55:28 | 2025-01-06 08:47:20 | 2025-01-08 08:22:05 | Akkem, Masthan
B312-2510899 | Decom_Ashburn_Training-physicalVMs_12.05.24 | 3 | GTO | 2025-01-02 17:39:29 | 2025-01-06 07:54:21 | 2025-01-06 08:45:57 | 2025-01-08 08:22:25 | Akkem, Masthan
B312-2520174 | Decom_Chicago_Decom FORELABS Secondary_16-Dec-2024 | 1 | Other | 2025-02-18 16:26:52 | 2025-02-27 19:15:30 | 2025-02-27 19:15:30 | 2025-03-17 09:54:36 | Akkem, Masthan
B312-2521640 | Decom_Ashburn_Decom AMAGC Servers_12.17.2024 | 3 | Security | 2025-01-08 16:37:39 | 2025-01-09 13:19:36 | 2025-01-22 10:21:01 | 2025-01-23 13:10:26 | Hoofnagle, James
B312-2634947 | Decom_Hillsboro_Verint_Lab_01.06.25 | 5 | Other | 2025-01-08 16:30:58 | 2025-01-09 13:29:53 | 2025-01-22 10:55:39 | 2025-01-28 12:19:53 | Akkem, Masthan
B312-2660914 | Decom_PA_T0HyperV01_DL360_01.10.25 | 1 | GTO | 2025-01-14 14:33:58 | 2025-01-21 13:54:26 | 2025-01-21 13:54:26 | 2025-01-21 13:54:31 | Herman, Gary
B312-2772090 | Decom_Decomm_HO__Singleview_2servers_27/01/2025 | 2 | Network (DCN) | 2025-03-25 15:58:51 | 2025-03-25 19:33:02 | 2025-03-25 19:33:02 | 2025-03-25 19:38:51 | Grewal, Pawan (Contractor)
B312-2775285 | Decom_Ashburn_cowildat-as-a1p.cable.co_01.28.25 | 1 | Comcast Business Services | 2025-03-17 14:30:01 | 2025-03-25 10:47:51 | 2025-03-25 10:47:51 | 2025-03-25 10:49:14 | Bhogle, Dhananjay (Contractor)
B312-2788500 | Decom_Westchester_T0HyperV02_DL360_Gen10+_01.29.25 | 1 | GTO | 2025-01-30 14:07:21 | 2025-01-30 19:01:24 | 2025-01-30 19:01:24 | 2025-01-30 19:05:46 | Herman, Gary
B312-2820079 | Decom_Decomm_Potomac__BDI_03/02/2025 | 1 | GTO | 2025-02-18 16:51:57 | 2025-02-25 12:12:43 | 2025-03-03 06:56:11 | 2025-03-14 05:39:19 | Kathirvel, Madhumitha
B312-2848551 | Decom_Potomac_wtpdb-po-p02a.cable.comc_02.08.25 | 1 | GTO | 2025-02-18 16:55:56 | 2025-02-25 14:39:33 | 2025-03-18 13:55:36 | 2025-03-25 19:30:27 | Grewal, Pawan (Contractor)
B312-2848554 | Decom_Potomac_wtpdb-po-p02b.cable.comc_02.08.25 | 1 | GTO | 2025-02-25 14:25:28 | 2025-02-25 14:25:55 | 2025-03-18 13:56:15 | 2025-03-25 19:32:08 | Grewal, Pawan (Contractor)
B312-2855010 | Decom_WC_ERONE_02.14.25 | 2 | GTO | 2025-02-20 17:03:07 | 2025-03-17 09:37:58 | 2025-03-17 12:52:11 | 2025-03-26 11:10:44 | Akkem, Masthan
B312-2859129 | Decom_AS_DLP AS_2.19.25 | 2 | Security | 2025-02-20 17:20:28 | 2025-02-25 09:28:28 | 2025-02-25 09:28:29 | 2025-02-25 09:40:46 | Akkem, Masthan
B312-2859130 | Decom_CH_DLP CH_2.19.25 | 5 | Security | 2025-02-20 17:26:37 | 2025-02-25 09:29:18 | 2025-02-25 09:29:19 | 2025-02-25 09:40:38 | Akkem, Masthan
B312-2864067 | Decom_Potomac_West Div Veeam Decom_02.24.2025 | 1 | Division (West) | 2025-02-27 16:36:23 | 2025-03-17 12:23:57 | 2025-03-17 12:23:57 | 2025-03-27 15:03:14 | Yacko, Adam
B312-2868534 | Decom_WC__BSDRESDB-WC-A1P server_2/28/2025 | 1 | GTO | 2025-02-28 20:03:11 | 2025-03-19 08:53:41 | 2025-03-19 08:53:41 | 2025-03-25 10:59:05 | Chakraborty, Siddhartha (Contractor)
B312-2870073 | Decom_CH2_DX_EQDP_MINTEK_EOL_03/03/2025 | 2 | GTO | 2025-04-03 17:20:00 | 2025-04-04 08:06:38 | 2025-04-14 13:50:14 | 2025-04-18 10:06:43 | Akkem, Masthan
B312-2885187 | Decom_Ashburn NDC_PAM servers decom_03.14.25 | 4 | Security | 2025-03-24 15:32:41 | 2025-03-26 14:27:22 | 2025-03-26 14:27:22 | 2025-03-26 14:31:52 | Akkem, Masthan
B312-2886916 | Decom_Chicago NDC_PAM server decom_03.17.25 | 2 | Security | 2025-03-25 15:28:00 | 2025-03-26 15:00:27 | 2025-03-26 15:00:28 | 2025-03-26 15:00:34 | Akkem, Masthan
B312-2887054 | Decom_Hillsboro_NDC_PAM server decom_03.17.25 | 4 | Security | 2025-03-25 16:04:27 | 2025-03-26 14:58:47 | 2025-03-26 14:58:47 | 2025-03-26 14:58:59 | Akkem, Masthan
B312-2923694 | Decom_Hillsboro_West Veeam Decomm_04.10.25 | 1 | Division (West) | 2025-05-07 15:43:07 | 2025-05-13 21:15:17 | 2025-05-13 21:15:18 | 2025-05-27 19:14:12 | Page, Tim
B312-3007682 | Decom_Ashburn_EBI Market Intell Decom_04.30.25 | 1 | Other | 2025-05-27 16:44:33 | 2025-05-28 10:44:00 | 2025-06-02 07:11:42 | 2025-06-09 07:57:55 | Akkem, Masthan
B312-2895019 | Decom_AS_DLP JMP_3.25.25 | 1 | Security | 2025-04-01 15:22:37 | 2025-04-02 08:46:58 | 2025-04-02 10:23:02 | 2025-04-03 11:37:39 | Akkem, Masthan
B312-2895025 | Decom_AS_DLP_3.25.25 | 3 | Security | 2025-04-01 15:27:20 | 2025-04-02 08:45:50 | 2025-04-04 17:07:38 | 2025-04-08 11:33:26 | Akkem, Masthan
B312-2903963 | Decom_WC_DLP JMP_4.2.25 | 1 | Security | 2025-04-03 17:31:20 | 2025-04-04 08:04:11 | 2025-04-04 08:26:45 | 2025-04-04 12:19:44 | B, Mukesh
B312-2910198 | Decom_Dry Creek_vmsapp-dcf-4p_04.04.25 | 1 | Security | 2025-04-09 15:28:54 | 2025-04-17 15:20:52 | 2025-04-17 15:20:53 | 2025-04-18 09:56:43 | Akkem, Masthan
B312-2919402 | Decom_Hillsboro_AMAGNVR-HO Servers_04.07.25 | 3 | Security | 2025-04-09 15:31:55 | 2025-04-17 15:20:41 | 2025-04-17 15:20:41 | 2025-04-18 09:44:12 | Akkem, Masthan
B312-2902163 | Decom_WC_SecureLogix-Decom_04.01.25 | 3 | GTO | 2025-04-04 05:34:08 | 2025-04-04 08:06:20 | 2025-04-16 06:31:29 | 2025-04-18 09:57:48 | Akkem, Masthan

## Raw SQL Results
Full ID | Title | *Number of Devices | *Line of Business | Server Review - Windows: Started | Server Review - Windows: Completed | Power Down - Windows: Started | Power Down - Windows: Completed | Power Down - Windows: Completer